## Nouveau parc - Conformités
1.Compléter les lignes suivantes (cases jaunes) 2.Copié les données du tableau 3.Coller dans la page d'import de Bluepoint en séléctionnant le module "Compliance" pour le premier tableau 4.Importer ! 5. Répéter les étapes 3 & 4 pour les tâches dans le midule "Tasks"
Site | ROUS
Centrales | ROUS-ECP001-METER001;ROUS-ECP001-METER002
CAGA | kevin.clement@edf-re.fr
Date prévisionnelle OR3 | 2021-06-01
Date prévisionnelle GA1 | 2022-01-01
1 - Ajouter les "Compliance" via le module d'import | https://www.bluepoint.io/import/
string | string (MANDATORY) | string | string - select | string - multiple select possible, separate by semi-colon | string | string - multiple select possible, separate by semi-colon | string - multiple select possible, separate by semi-colon | string - multiple select possible, separate by semi-colon | string | string - multiple select possible, separate by semi-colon | string - multiple select possible, separate by semi-colon | string - boolean | date string | string - boolean | numeric | string - select | numeric | string - select | numeric | date string | numeric | string - boolean | numeric | string - boolean | numeric
[6 empty] | Only fill out if "Compliance Type" is Regulatory. Provide either Plant(s), Location(s), or Portfolio(s) |  |  | Only fill out if "Compliance Type" is Contract |  |  |  | Only fill out if "Milestone Based" is No | Only fill out if "Milestone Based" is Yes | [5 empty] | Either "Repeat Until (Date)" or "Occurs (Times)" field, but not both |  |  | Only fill out if "Send Reminder to user/s in Responsibility" is Yes |  | Only fill out if "Send Reminder to user/s in Escalation" is Yes
Unique identifier - leave blank to generate one automatically | Unique name | Compliance related task | Options: - Regulatory - Contract |  |  | Plant ID(s) of existing plant(s) (or projects if "Project Development" module enabled) | Location ID(s) of existing Location(s) | Portfolio Name(s) of existing Portfolio(s) | Contract Name of an existing Contract | Email address of an Activated BluePoint user(s) | Email address of an Activated BluePoint user(s) | Options: - No, if based on Date - Yes, if based on Milestone |  | Existing Milestone as listed under the relevant Plant(s) | Number of days | Options: - Before - After | Number of days before compliance deadline | Options: - Annually - Monthly - Weekly - Daily | Whole number |  | Whole number | Yes / No |  | Yes / No
Identifier | Compliance | Task Name | Type | Tags | Description | Plant IDs | Locations | Portfolios Names | Contract | Responsibility | Escalation | Milestone Based | Compliance Deadline | Milestone Type | Milestone Deadline (days) | Milestone Deadline Type | Internal Deadline (days) | Frequency | Frequency Every | Repeat Until (Date) | Occurs (Times) | Send Reminder to user/s in Responsibility | Days before internal deadline | Send Reminder to user/s in Escalation | Days before deadline
ROUS-Suivi_annee_1 | OR3 | Signature PV OR3 | Regulatory | OR3 | Listes des tâches liées à la réception d'actifs |  | ROUS |  | Land Lease Agreement Plant A001 | kevin.clement@edf-re.fr |  | Yes |  | Mise en Service Industrielle (MSI) | 365 | After | 180 |  | 1 |  |  | No | 30 | No
ROUS-Suivi_annee_10 | GA1 | Validation GA1 | Regulatory | GA1 | Listes des réserves listées en OR3 |  | ROUS |  |  | kevin.clement@edf-re.fr |  | Yes |  | Mise en Service Industrielle (MSI) | 3652 | After | 3400 |  | 1 |  |  | No | 30 | No
ROUS-PDP | PDP annuelle | Renouvellement PDP | Regulatory | H&S | Signature et renouvellement annuel du plan de prévention |  | ROUS |  | O&M Agreement Plant A001 | kevin.clement@edf-re.fr |  | No |  |  |  |  | 180 |  | 1 |  |  | No | 30 | No
ROUS-VIC | VIC | Plannification VIC | Regulatory | H&S | Organisation de la Visite d'Inspection Commune |  | ROUS |  |  | kevin.clement@edf-re.fr |  | No |  |  |  |  | 180 |  | 2 |  |  | No | 30 | No
2 - Ajouter toutes les tâches
numeric | string (MANDATORY) | string (multiple users separated by ;) | date | string - select | string - select | string (multiple tags separated by ;) |  | date | date | string | date | string | string (one or multiple plants separated by ;) | string (one or multiple portfolios separated by ;) | numeric | string - select | string
General Fields | [12 empty] | Regular tasks |  | Compliance tasks | Event tasks | Project tasks
Use only to update Tasks. (Task IDs can be taken from BluePoint for existing Tasks). BluePoint automatically assigns the ID to new Task | Unique Task name | Existing User names |  | Options: - regular (default) - compliance - event - project | Options: - Low - Medium (default) - High |  |  |  |  | Options (in lower case): - open - closed |  |  | Plant(s) OR Portfolio(s) is MANDATORY if "Type" is blank or Regular Plant is MANDATORY if "Type" is Milestone |  | MANDATORY if "Type" is Compliance | MANDATORY if "Type" is Event | MANDATORY if "Type" is Project
[9 empty] | MANDATORY if "Type" is Project |  |  |  | Plant ID of an existing plant (or project if "Project Development" module enabled) | Portfolio name of an existing portfolio | Compliance ID of an exisiting compliance | Event ID of an exisiting event
Task ID | Name | Responsibility | Due date | Type | Priority | Tags | Latest update | Internal deadline | Start date | Status | Date Closed | Notes | Plant identifier(s) | Portfolios | Compliance ID | Event ID | Project | Location Identifier
| Récpetion et validation des rapports d'insection | 0 | 2021-06-01 | compliance |  | OR3 |  |  |  | open |  |  | 0 |  | ROUS-Suivi_annee_1
| Validation Fiche SEE | 0 | 2021-06-01 | compliance |  | OR3 |  |  |  | open |  |  | 0 |  | ROUS-Suivi_annee_1
| Rédaction du PV de prise en charge GA | 0 | 2021-06-01 | compliance |  | OR3 |  |  |  | open |  |  | 0 |  | ROUS-Suivi_annee_1
| Préparation du contrat O&M parc | 0 | 2021-06-01 | compliance |  | OR3 |  |  |  | open |  |  | 0 |  | ROUS-Suivi_annee_1
| Prépration du contrat O&M poste | 0 | 2021-06-01 | compliance |  | OR3 |  |  |  | open |  |  | 0 |  | ROUS-Suivi_annee_1
| Communication de la date de passage en exploitation aux prestaires externes | 0 | 2021-06-01 | compliance |  | OR3 |  |  |  | open |  |  | 0 |  | ROUS-Suivi_annee_1
| Faire signer le PV de prise en charge avec la liste des réserves actualisée | 0 | 2021-06-01 | compliance |  | OR3 |  |  |  | open |  |  | 0 |  | ROUS-Suivi_annee_1
| Activer les contrat O&M et GA en date de réception | 0 | 2021-06-01 | compliance |  | OR3 |  |  |  | open |  |  | 0 |  | ROUS-Suivi_annee_1

## Nouveau parc - Tâches
| Centrale | ANPA
| CAGA | kevin.clement@edf-re.fr
numeric | string (MANDATORY) | string (multiple users separated by ;) | date | string - select | string - select | string (multiple tags separated by ;) |  | date | date | string | date | string | string (one or multiple plants separated by ;) | string (one or multiple portfolios separated by ;) | numeric | string - select | string
General Fields | [12 empty] | Regular tasks |  | Compliance tasks | Event tasks | Project tasks
Use only to update Tasks. (Task IDs can be taken from BluePoint for existing Tasks). BluePoint automatically assigns the ID to new Task | Unique Task name | Existing User names |  | Options: - regular (default) - compliance - event - project | Options: - Low - Medium (default) - High |  |  |  |  | Options (in lower case): - open - closed |  |  | Plant(s) OR Portfolio(s) is MANDATORY if "Type" is blank or Regular Plant is MANDATORY if "Type" is Milestone |  | MANDATORY if "Type" is Compliance | MANDATORY if "Type" is Event | MANDATORY if "Type" is Project
[9 empty] | MANDATORY if "Type" is Project |  |  |  | Plant ID of an existing plant (or project if "Project Development" module enabled) | Portfolio name of an existing portfolio | Compliance ID of an exisiting compliance | Event ID of an exisiting event
Task ID | Name | Responsibility | Due date | Type | Priority | Tags | Latest update | Internal deadline | Start date | Status | Date Closed | Notes | Plant identifier(s) | Portfolios | Compliance ID | Event ID | Project | Location Identifier | Milestone ID | Milestone deadline type | Milestone deadline | Milestone duration
| Récpetion et validation des rapports d'insection | kevin.clement@edf-re.fr | 1970-01-01 | milestone |  | OR3 |  |  |  | open |  |  | ANPA | [5 empty] | 53666 | before | 15 | 90
| Validation Fiche SEE | kevin.clement@edf-re.fr | 1970-01-01 | milestone |  | OR3 |  |  |  | open |  |  | ANPA | [5 empty] | 53666 | before | 15 | 90
| Rédaction du PV de prise en charge GA | kevin.clement@edf-re.fr | 1970-01-01 | milestone |  | OR3 |  |  |  | open |  |  | ANPA | [5 empty] | 53666 | before | 15 | 90
| Préparation du contrat O&M parc | kevin.clement@edf-re.fr | 1970-01-01 | milestone |  | OR3 |  |  |  | open |  |  | ANPA | [5 empty] | 53666 | before | 15 | 90
| Prépration du contrat O&M poste | kevin.clement@edf-re.fr | 1970-01-01 | milestone |  | OR3 |  |  |  | open |  |  | ANPA | [5 empty] | 53666 | before | 15 | 90
| Communication de la date de passage en exploitation aux prestaires externes | kevin.clement@edf-re.fr | 1970-01-01 | milestone |  | OR3 |  |  |  | open |  |  | ANPA | [5 empty] | 53666 | by | 0 | 0
| Faire signer le PV de prise en charge avec la liste des réserves actualisée | kevin.clement@edf-re.fr | 1970-01-01 | milestone |  | OR3 |  |  |  | open |  |  | ANPA | [5 empty] | 53666 | by | 0 | 0
| Activer les contrat O&M et GA en date de réception | kevin.clement@edf-re.fr | 1970-01-01 | milestone |  | OR3 |  |  |  | open |  |  | ANPA | [5 empty] | 53666 | by | 0 | 0